## Sheet1
Phase | Task | Start Date | Duration (days) | End Date | Effort (man-hours) | Who is doing it? | Responsible Person | Team
plan | making plan for tasks | 2016-11-04 | 3 | 2016-11-07 | 1 | Bojidara | Alena | Alena
plan | approval of the plan | 2016-11-07 | 4 | 2016-11-11 | 2 | whole team +rashkov | bojidara | Bojidara
html | making the questions | 2016-11-11 | 3 | 2016-11-14 | 10 | whole team | Gergana | Valeriq
plan | name of the website | 2016-11-11 | 7 | 2016-11-18 | 2 | whole team | Alena | Gergana
html | making the front page | 2016-11-11 | 7 | 2016-11-18 | 10 | Desislava, Alena | Bojidara | Desislava
design | making avatars | 2016-11-18 | 14 | 2016-12-02 | 10 | Gergana | Liq | Liq
design | making design of questions | 2016-11-25 | 7 | 2016-12-02 | 10 | Liq | Valeriq
design | design of the front page | 2016-11-25 | 7 | 2016-12-02 | 15 | Liq, Gergana | Desislava
approval | approval of the website | 2016-12-02 | 7 | 2016-12-09 | 1 | whole team
approval | changing (if there is need) | 2016-12-09 | 16 | 2016-12-25 | 10 | whole teem
test | testing | 2016-12-25 | 12 | 2017-01-06 | 1 | NPMG | Gergana
popularity | spread to other schools | 2017-01-06 | 14 | 2017-01-20 | 5 | whole team | Valeriq
popularity | find sponsors | 2017-01-20 | 7 | 2017-01-27 | 40 | Valeriq | Desislava
future tasks | chat room |  | 0
future tasks | joke of the day |  | 0
future tasks | teachers progress |  | 0